## Daily Standup
Daily Stand-up Report - Neha Kumari - Smart Asset Management System (PrimXact)
Date | Name | Project | What did I complete yesterday? | What am I working on today? | Are there any blockers?
2026-01-08 | Neha Kumari | Smart Asset Management System | Internship started today. | Project requirements analysis, SRS document planning, and technology stack finalization. | None
2026-03-08 | Neha Kumari | Smart Asset Management System | Project requirements analysis Technology stack finalization. Initial SRS document structure and project planning. | Completed the Software Requirements Specification (SRS) document. Designed the database structure and defined table relationships. Planned the user interface screens and future system enhancements. | none
2026-04-08 | Neha Kumari | Smart Asset Management System | Completed the Software Requirements Specification (SRS) document. Prepared the database design and project structure | Set up the Node.js development environment. Configured the Express.js backend project. Installed the required npm packages. Initialized the Git repository and pushed the initial project to GitHub. Created and verified the backend server successfully. | none
2026-05-08 | Neha Kumari | Smart Asset Management System | Set up the Node.js development environment. Configured the Express.js backend project. Installed the required npm packages. Successfully verified the backend server | Installed and configured XAMPP. Created the MySQL database (smart_asset_db). Created the users table. Connected the Node.js backend with the MySQL database. Successfully verified the database connection | none
2026-06-08 | Neha Kumari | Smart Asset Management System | Installed and configured XAMPP. Created the MySQL database. Created the users table. Connected the Node.js backend with the MySQL database. Successfully verified the database connection. | Created the assets table. Created the employees table. Defined the database relationships in the SRS document. Designed and exported the ER Diagram (PNG & PDF). Initialized Git version control and updated the project repository on GitHub | none
2026-07-08 | Neha Kumari | Smart Asset Management System | Created the assets table. Created the employees table. Defined the database relationships. Designed and exported the ER Diagram. | Created the categories,vendors,assignments and maintenance table. Prepared the database schema script (schema.sql). Updated the project repository with the latest database changes. | none
2026-08-08 | Neha Kumari | Smart Asset Management System | Completed the database design by creating the remaining project tables. Updated the complete database schema with all required entities and relationships. Finalized the ER Diagram and verified all table relationships. Updated the SRS document with the final ER Diagram and database details. Uploaded the updated documentation (SRS and ER Diagram) to the GitHub repository. Design & Planning deliverables | Started backend development by implementing the Authentication module. Developed secure Login API using bcrypt password hashing and JWT authentication. Implemented protected routes with role-based authorization for Admin. Created the Employee Management module structure (Models, Controllers, and Routes). Integrated Employee routes with the server and successfully tested Authentication APIs and the Employee API using Thunder Client. Updated the GitHub repository with the latest backend implementation. | none
2026-10-08 | Neha Kumari | Smart Asset Management System | Started backend development by implementing the Authentication module. Developed a secure Login API using bcrypt password hashing and JWT authentication. Implemented protected routes with role-based authorization for Admin. Created the Employee Management module structure including Models, Controllers, and Routes. Integrated Employee routes with the server and successfully tested the Authentication APIs and Employee API using Thunder Client. | Implemented the Asset Management module, including Asset Model, Controller, Routes, and CRUD APIs. Successfully tested Create, Read, Update, and Delete operations for Assets using Thunder Client.Implemented the Category Management module with Model, Controller, Routes, and server integration.Successfully tested Category GET, POST, PUT, and DELETE APIs. Implemented the Vendor Management module with complete CRUD functionality. Successfully tested Vendor GET, POST, PUT, and DELETE APIs using Thunder Client. Updated and connected the required backend routes with the main server. | Faced a few backend configuration and routing issues while integrating the modules and testing the APIs. Encountered some database connectivity and API testing issues during development. All encountered issues were identified and successfully resolved, and the implemented modules are now working as expected. no blockers at the moment.
2026-11-08 | Neha Kumari | Smart Asset Management System | Implemented the Asset Management module, including Asset Model, Controller, Routes, and CRUD APIs. Successfully tested Create, Read, Update, and Delete operations for Assets using Thunder Client. Implemented the Category Management module with Model, Controller, Routes, and server integration. Successfully tested Category GET, POST, PUT, and DELETE APIs. Implemented the Vendor Management module with complete CRUD functionality. Successfully tested Vendor GET, POST, PUT, and DELETE APIs using Thunder Client. Updated and connected the required backend routes with the main server. | Started implementing the Asset Assignment module with Model, Controller, and Routes. Integrated Assignment routes with the backend server and successfully tested the GET Assignment API. Verified the relationship between Assets and Employees required for assignments. Added and verified an Employee record required for the Assignment module. Successfully created an Asset Assignment linking an Asset with an Employee. Tested and verified the Assignment data using the GET API through Thunder Client. Successfully implemented and tested the Assignment Update (PUT) API, including updating the return date and assignment status. Continuing the remaining Assignment CRUD verification. | none
2026-12-08 | Neha Kumari | Smart Asset Management System | Completed the Assignment Management module by implementing and testing the complete assignment workflow. Implemented APIs for creating, viewing, updating, and deleting asset assignments. Tested asset assignment and return functionality and verified the related database records. Resolved foreign key issues during testing by verifying the required asset and employee records before creating assignments. | Continued backend development by completing the Maintenance Management module, including its Model, Controller, and Routes. Implemented and tested the complete Maintenance CRUD functionality for adding, viewing, updating, and deleting maintenance records. Developed and integrated the Software License Management module and successfully tested its complete CRUD operations. Implemented the Audit Logs module with Model, Controller, and Routes and tested its complete CRUD functionality. Resolved a temporary MySQL connection issue during Audit Logs testing and successfully restarted and verified the server and database connection. Updated the GitHub repository with the completed Maintenance, Software License, and Audit Logs backend modules. | none
13/8/2026 | Neha Kumari | Smart Asset Management System | Completed and tested the Maintenance, Software License, and Audit Logs modules, including their CRUD APIs, database integration, and GitHub updates. Resolved a temporary MySQL connection issue during testing. | Completed and tested the Warranty Management CRUD module. Implemented JWT-based authentication with secure password hashing using bcrypt. Implemented Login API with JWT token generation and expiry. Added authentication and role-based authorization middleware. Protected backend APIs and tested token-based access through Thunder Client. Updated and pushed the latest backend changes to GitHub. | none
15/8/2026 | Neha Kumari | Smart Asset Management System | Completed Warranty Management and implemented JWT authentication, password hashing, login/token generation, role-based authorization, and API protection with testing. | Developed the Admin Dashboard backend with asset, employee, vendor, category, warranty, and software license statistics. Added asset status breakdown and warranty/software license expiry alerts for better monitoring. Tested the dashboard and expiry-alert functionality through Thunder Client and verified the database results. Committed and pushed the dashboard enhancements to GitHub. | none
17/8/2026 | Neha Kumari | Smart Asset Management System | Continued backend and frontend integration for the Warranty & Licenses module. Completed the Admin Dashboard with asset statistics and status distribution. Added warranty/license expiry alert functionality. Tested the APIs and database operations using Thunder Client. Verified the data flow between the frontend, REST APIs and MySQL database. Committed and pushed the completed work to GitHub. | Completed the Employees module with employee listing, search, status filtering and CRUD operations. Completed the Assignments module with asset/employee selection, assignment tracking, search/filtering and CRUD operations. Completed the Maintenance module with maintenance records, asset selection, status/details management and CRUD operations. Completed the Warranty & Licenses frontend, including separate Warranty and Software License management. Completed the Reports module and connected it with the existing asset, employee, assignment and maintenance data. Completed the Audit Logs module with viewing, adding, editing, deleting and refreshing audit records. Fixed multiple frontend routing, file-path, CSS and JavaScript integration issues so the modules open correctly with the Aegis AssetOps design. Successfully opened and verified the major modules through the local server. | none
18/8/2026 | Neha Kumari | Smart Asset Management System | Completed the Employees module with employee listing, search, status filtering and CRUD operations. Completed the Assignments module with asset/employee selection, assignment tracking, search/filtering and CRUD operations. Completed the Maintenance module with maintenance records, asset selection, status/details management and CRUD operations. Completed the Warranty & Licenses frontend, including separate Warranty and Software License management. Completed the Reports module and connected it with the existing asset, employee, assignment and maintenance data. Completed the Audit Logs module with viewing, adding, editing, deleting and refreshing audit records. Fixed multiple frontend routing, file-path, CSS and JavaScript integration issues so the modules open correctly with the Aegis AssetOps design. Successfully opened and verified the major modules through the local server. | Fixed a database error preventing asset deletion caused by foreign key constraints. Added the missing warranties table to the database and updated the schema accordingly. Implemented real QR code generation for assets and fixed the QR code display in the asset table. Added security hardening to the backend using Helmet and rate-limiting to prevent brute-force login attempts. Added a CSV export feature for the asset inventory. Set up the structure for automated warranty/license expiry email alerts. Added a visual asset status chart to the Admin Dashboard. | none
19/8/2026 | Neha Kumari | Smart Asset Management System | Fixed database deletion bug and added missing warranties table Implemented real QR code generation and fixed QR display in assets table Added security hardening (Helmet, rate-limiting) Added CSV export for asset inventory Set up structure for automated warranty/license expiry email alerts Added a visual asset status chart to the Admin Dashboard | Improved database connection stability using connection pooling Configured and tested Gmail expiry alert emails Connected frontend Expiry Alerts panel to live warranty/license data Added Depreciation Report (backend calculation + frontend display) all 8 core project features now complete | none
20/8/2026 | Neha Kumari | Smart Asset Management System | Improved database connection stability using connection pooling Configured and tested Gmail expiry alert emails Connected frontend Expiry Alerts panel to live warranty/license data Added Depreciation Report (backend calculation + frontend display) all 8 core project features now complete | Fixed database connection stability and configured Gmail expiry alerts Connected frontend Expiry Alerts panel to live data Added Depreciation Report (backend + frontend) | none
21/8/2026 | Neha Kumari | Smart Asset Management System | Fixed database connection stability and configured Gmail expiry alerts Connected frontend Expiry Alerts panel to live data Added Depreciation Report (backend + frontend) | Added dark mode toggle across all pages Built Edit Profile page (update name/email, change password) Implemented automatic audit logging for asset actions (create/update/delete) Improved QR codes to encode a direct scannable link to the asset page instead of just the code Added a global search bar (assets + employees) to the Command Center | none
22/8/2026 | Neha Kumari | Smart Asset Management System | Added dark mode toggle across all pages Built Edit Profile page (update name/email, change password) Implemented automatic audit logging for asset actions (create/update/delete) Improved QR codes to encode a direct scannable link to the asset page instead of just the code Added a global search bar (assets + employees) to the Command Center | Implemented role-based access control: Admin, Sub-Admin, Report Viewer, and Reader roles Built User Management module (Admin can add/delete login accounts and assign roles) Built a Permissions overview page showing what each role can access Fixed missing authentication/authorization checks on Assignments, Maintenance, Warranty, Software License, and Audit Log routes Added asset status-change history tracking in the audit log | none
24/8/2026 | Neha Kumari | Smart Asset Management System | Implemented role-based access control: Admin, Sub-Admin, Report Viewer, and Reader roles Built User Management module and Permissions overview page Fixed missing authentication/authorization checks on Assignments, Maintenance, Warranty, Software License, and Audit Log routes Added asset status-change history tracking in the audit log | Rebuilt the ER Diagram with 1NF-4NF normalization notes embedded directly in the image Redesigned the UI with a professional icon set, refined typography, and consistent component styling across all pages Redesigned the login page with a modern, industry-style visual layout Added report export metadata (generated by, date, and time) to printed reports Fixed a database connection stability issue (IPv4/IPv6 host mismatch) Fixed the site favicon and button focus styling | none
25/8/2026 | Neha Kumari | Smart Asset Management System | Rebuilt the ER Diagram with 1NF-4NF normalization notes embedded directly in the image Redesigned the UI with a professional icon set, refined typography, and consistent component styling Redesigned the login page with a modern, industry-style visual layout Added report export metadata (generated by, date, and time) to printed reports Fixed a database connection stability issue and the site favic | Fixed CSS styling gaps across Employees, Assignments, Maintenance, Warranty, and Audit Logs pages to match the professional design system Fixed button focus states and loading/empty-state animations site-wide Updated the SRS document with database normalization, entity relationship cardinality, security implementation, and a full summary of all implemented enhancements | none
27/8/2028 | Neha Kumari | Smart Asset Management System | Fixed CSS styling gaps across Employees, Assignments, Maintenance, Warranty, and Audit Logs pages Fixed button focus states and loading/empty-state animations site-wide Updated SRS with normalization, cardinality, and full feature summary Created full Technical Documentation covering architecture, API endpoints, and setup | Built an Email Settings module — Admin now configures their own Gmail credentials through a secure page, with the password encrypted before being stored in the database (removed hardcoded email config) Fixed expiry alerts to email the employee currently assigned to the asset, plus the admin, instead of one fixed address Added a new automated alert for upcoming asset return dates (in addition to warranty/license expiry) Extended the Command Center dashboard to display upcoming asset returns alongside expiry alerts | none
28/8/2026 | Neha Kumari | Smart Asset Management System | Built an Email Settings module — Admin now configures their own Gmail credentials securely (encrypted storage) Fixed expiry alerts to notify the currently assigned employee, plus the admin Added automated alerts for upcoming asset return dates Extended the Command Center dashboard to display upcoming asset returns | Added a Bulk CSV Import feature for assets, allowing multiple asset records to be uploaded at once instead of manual one-by-one entry Replaced remaining emoji/text icons (dark mode toggle, notifications, dashboard metric cards) with the professional icon set across all pages Done with final SRS and technical document | none